## Sheet1
Task Name | Status | Description | Time Allotted (hrs)
Planning and research |  | Sketching out some design ideas, researching technologies | 0.4
Writing Requirement Specification |  | Parse requirements from assignment, format requirements into a table, write descriptions for each. | 0.3
Writing High-Level Design |  | Take results of research and planning and put them into a document that is easy to read | 0.6
Setting up the environment for development |  | Get a project set up and install all dependencies. | 0.7
Create and parse a configuration file |  | Use Boost.PropertiesTree to parse a .ini file. Possible configuration options include: heartbeat interval and default comms port | 0.5
Write the CN heartbeat server and client |  | CNs should be able to send a heartbeat signal on a fixed interval. They should also be able to respond to heartbeats from other CNs by setting up a TCP socket. | 1
Write logic for keeping track of neighboring nodes |  | The CN should be able to keep track of information about all of its neighboring nodes by maintaining a set of node information objects. | 1
Write python web server |  | Create a simple python web server that will display information about each node on the current machine and their neighbors. It will also respond to three commands: stopNode, startNode, and configureNode. This will eventually use a C++ module. | 1.5
Write actions for web server |  | The handlers for the various actions coming from the web server will be handled by a C++ class. There should be three methods in this class: void stopNode(UUID), void startNode(UUID), void configureNode(UUID, NodeConfig) | 1
Write C++ wrapper for web server |  | This C++ class should handle starting and stopping the python web server as well as handling callbacks for actions. | 1
Write front end code for the web view |  | Using HTML, CSS, and JS (jQuery) write a web page that will be served by python. At a minimum, this page should show a dropdown with an entry for each CN on the machine and a table with a row for each neighbor of said machine with 4 columns. These columns should be: ID, latency, bandwidth, and the fourth should contain a dropdown with three choices (start, stop, and configure) plus a submit button. | 1.5
Test |  | Unit tests will be written and run throughout the development process, but a comprehensive integration test should be performed at the end of the project. | 0.5
|  | TOTAL= | 10